BvLogic

TEMPLATE

Change Request

| Document ID | BVL-CE54C1 |
| --- | --- |
| Version | 1.0 |
| Status | Published |
| Owner | BvLogic Knowledge Management |
| Classification | Public |
| Issued | 18 August 2026 |
| Next review | 18 August 2027 |
| Document type | Template |

Contents

One page. The temptation is to expand this form until it deters requests, which works, and

produces undocumented changes rather than fewer changes.

Change ref: CR-____  Date raised: _______  Raised by: _______________ Project: _______________

# What is requested

Change: _______________

Why, and why now: _______________

Urgency: routine / next release / urgent, justification: _______________

Is this a change or a defect? change / defect against requirement ____ / clarification

A defect against an agreed requirement is not a change. A requirement that was never specified

is a change. Reclassifying missed requirements as defects to dodge this conversation destroys

trust, and so does the reverse.

# Impact assessment

Not assessed by the person requesting it.

| Development effort |  |
| --- | --- |
| Retesting required |  |
| Documentation and requirement updates |  |
| Regression risk |  |
| Schedule impact |  |
| Cost impact |  |
| Risks introduced |  |
| Assessed by |  |

What this displaces: _______________

The displacement line is what makes the decision real. On a fixed-capacity project every addition is a substitution: naming what will not happen converts an abstract approval into a trade-off, and it changes decisions.

If effort is genuinely unknown: say so and offer to assess properly. A number invented in a meeting becomes a commitment by the end of it.

# Decision

| Decision | approve / reject / defer until ___ |
| --- | --- |
| Decided by |  |
| Date |  |
| Rationale |  |

# After approval: update these

[ ] Requirements (BRD (bvlogic.com/pmo/brd/) / FRD (bvlogic.com/pmo/frd/) / SRS (bvlogic.com/pmo/srs/))

[ ] Traceability matrix (bvlogic.com/pmo/rtm/)

[ ] Test scope and UAT (bvlogic.com/pmo/uat/) criteria

[ ] Plan and budget

[ ] Risk register (bvlogic.com/pmo/risk-register/)

[ ] Stakeholders informed

A change approved but not reflected in the artefacts is how documents and reality diverge.

---

# Delegated Authority

Set thresholds so small changes clear in a day. A process that takes three weeks to approve a two-hour change will be bypassed, and the bypassing will not be visible.

| Size | Decided by | Target turnaround |
| --- | --- | --- |
| No cost or schedule impact, within scope | Project manager | Same day |
| Absorbed within contingency | PM, sponsor informed | 1 to 2 days |
| Material cost, schedule or scope impact | Sponsor | Weekly cycle |
| Beyond the charter boundary | Steering group | Scheduled |

Emergency path: who may approve ___________, evidence required ___________, documented within ___ hours afterwards.

---

# Change Register

| Ref | Summary | Raised | Decision | Schedule impact | Cost impact | Decided by |
| --- | --- | --- | --- | --- | --- | --- |
| CR-001 |  |  |  |  |  |  |

# Cumulative position: report at every review

| Changes raised |  |
| --- | --- |
| Approved |  |
| Rejected |  |
| Cumulative schedule impact |  |
| Cumulative cost impact |  |
| What has been dropped to absorb them |  |

This table is the one that matters and the one nobody volunteers. Fifteen individually reasonable changes have added eleven weeks; each was assessed alone, so nobody said so. Sponsors approve individually reasonable things and are generally grateful to see the aggregate.

If nothing has ever been rejected, the process is a recording mechanism rather than a control.

Notice

This document is published by BvLogic as general reference material. It is provided for information only and is not professional, financial, legal or tax advice, and no liability is accepted for decisions taken on the basis of it. Figures in worked examples are illustrative unless a source is cited. Verify anything time-sensitive against the live version at bvlogic.com before relying on it.