BvLogic

TEMPLATE

Cloud Migration Assessment: One Application

| Document ID | BVL-F40ABC |
| --- | --- |
| Version | 1.0 |
| Status | Published |
| Owner | BvLogic Knowledge Management |
| Classification | Public |
| Issued | 18 August 2026 |
| Next review | 18 August 2027 |
| Document type | Template |

Contents

Complete one of these per application, not one per programme. Migrations fail at the

application level, and the ones that hurt are always the application everybody assumed was

simple.

Application: _______________ Business owner: _______________  Technical owner: _______________ Date: _______

# 1. What it is

| What it does, in one sentence |  |
| --- | --- |
| Users (number, internal/external) |  |
| Business criticality | critical / important / routine |
| Hours it must be available |  |
| Acceptable downtime for the cutover |  |
| Who notices first if it stops |  |

If it disappeared for a day, what would actually happen? _______________

Ask this question of the business owner, not the technical owner. Roughly half of the

applications on a typical migration list turn out to be retirable, and retiring one is the

cheapest possible migration.

# 2. Current state

| Servers / instances |  |
| --- | --- |
| Operating system + version (still supported?) |  |
| Runtime + version |  |
| Database + version |  |
| Data volume today, growth per year |  |
| Licensing that follows the workload |  |

# 3. Dependencies: the part that breaks cutovers

| Depends on | Direction | Latency sensitive | Moving at the same time |
| --- | --- | --- | --- |
|  | in / out | yes / no | yes / no |

Hard-coded IP addresses, hostnames or file paths anywhere: _______________ Scheduled jobs that touch this system: _______________ Anything that connects to it that we do not control: _______________

The dependency nobody documents is the batch job on someone's machine. Ask the operations team, and ask what runs overnight.

# 4. Data gravity

| Data volume to move |  |
| --- | --- |
| Bandwidth available |  |
| Estimated transfer time at that bandwidth |  |
| Can the source stay writable during transfer | yes / no |
| How changes during transfer are reconciled |  |
| Residency or sovereignty constraints |  |

Data movement, not application compatibility, sets the schedule for most migrations. Calculate the transfer time before agreeing to a cutover window.

# 5. Migration pattern: pick one, record why

| Pattern | Meaning | Chosen |
| --- | --- | --- |
| Retire | Turn it off |  |
| Retain | Leave it where it is, for now |  |
| Rehost | Move as-is |  |
| Replatform | Move with modest changes (managed database, container) |  |
| Refactor | Rework for cloud services |  |
| Repurchase | Replace with a product |  |

Why this pattern: _______________ What we are explicitly NOT doing in this move: _______________

Doing a rehost and a refactor in one step means that when something breaks you cannot tell

which change caused it. Move it, stabilise it, then improve it.

# 6. Target state and cost

|  | Today | Target |
| --- | --- | --- |
| Compute |  |  |
| Storage |  |  |
| Database |  |  |
| Network / egress |  |  |
| Licences |  |  |
| Backup |  |  |
| Monthly total |  |  |

Costs that will appear only after go-live (egress, cross-zone traffic, log volume, non-production environments): _______________

# 7. Security and compliance

| Data classification |  |
| --- | --- |
| Personal data involved | yes / no |
| Encryption at rest / in transit |  |
| Who has access after the move |  |
| Logging and retention requirement |  |
| Sign-off required from |  |

# 8. Cutover plan

| Proposed window |  |
| --- | --- |
| Steps, in order |  |
| Point of no return |  |
| How we roll back, and until when |  |
| Who decides to roll back |  |
| Validation before declaring success |  |

Rollback tested on (date): _______

"We will roll back if needed" is not a plan unless someone has run it. Establish the point after which rollback is no longer possible, and make sure the decision-maker knows they are crossing it.

# 9. After go-live

[ ] Monitoring and alerts in place before the window, not after

[ ] Old environment kept for ___ days, then decommissioned (date: ______)

[ ] Backups running and one restore tested in the new location

[ ] Cost checked against estimate at day 30

[ ] Documentation and runbooks updated

[ ] Licences on the old platform cancelled

# Sign-off

|  | Name | Date |
| --- | --- | --- |
| Technical owner |  |  |
| Business owner |  |  |
| Security |  |  |
| Go / no-go |  |  |

Notice

This document is published by BvLogic as general reference material. It is provided for information only and is not professional, financial, legal or tax advice, and no liability is accepted for decisions taken on the basis of it. Figures in worked examples are illustrative unless a source is cited. Verify anything time-sensitive against the live version at bvlogic.com before relying on it.