BvLogic

TEMPLATE

Lessons Learned

| Document ID | BVL-D417A3 |
| --- | --- |
| Version | 1.0 |
| Status | Published |
| Owner | BvLogic Knowledge Management |
| Classification | Public |
| Issued | 18 August 2026 |
| Next review | 18 August 2027 |
| Document type | Template |

Contents

The deliverable is not this document. It is a change in how the next project runs. Three owned

actions beat thirty recorded findings, and actions that edit a template or a checklist beat

actions that ask people to remember something.

Project / phase: _______________  Session date: _______ Facilitator: _______________  Attendees: _______________

Held at: milestone / phase end / after a release / project close

Hold these at milestones, not only at close. By close, the early lessons are months old and the

people involved have moved on.

# 1. Timeline: facts first

Build this from records, not memory. Discussing causes before agreeing facts produces an argument about the facts, usually settled by whoever speaks most confidently.

| Date | What happened | Source |
| --- | --- | --- |

Planned vs actual: start ____ / ____, finish ____ / ____, budget ____ / ____, scope delivered ____%

# 2. The five questions

What did we expect, and what happened instead? _______________

Where did we lose time, and what was the queue? _______________

What did we discover late that we could have known earlier? _______________

What would we do identically? _______________

What surprised us? _______________

# 3. Findings

Separate these two, because they need different audiences and different actions.

## Specific to this project

| # | Finding | Cause (a condition, not a person) |
| --- | --- | --- |

## Systemic: will recur on every project until something changes

| # | Finding | Cause | Who can actually change this |
| --- | --- | --- | --- |

The systemic findings are the valuable ones and the uncomfortable ones, they usually implicate funding, governance, resourcing or dependencies rather than the delivery team. If your review only ever produces project-specific findings, the wrong people are in the room.

# 4. What worked

| # | What | Why it worked | Worth repeating? |
| --- | --- | --- | --- |

Reviews that only catalogue failures teach teams to avoid things without teaching them what to do, and they make the session unwelcome.

# 5. Actions: three is plenty

Prefer actions that change an artefact. The next team then benefits without knowing a lesson existed, which is the only mechanism that reliably survives.

| # | Action | Type | Owner | Due | Done |
| --- | --- | --- | --- | --- | --- |
| 1 |  | edit a template/checklist / change a process step / brief someone / escalate |  |  |  |
| 2 |  |  |  |  |  |
| 3 |  |  |  |  |  |

Findings we are NOT actioning, and why: _______________

Recording that honestly is better than assigning something to a role that will not act on it.

# 6. Handover to the next project

[ ] Templates or checklists edited (which: ____________)

[ ] Process step added or removed (which: ____________)

[ ] Outgoing PM briefed the incoming PM directly

[ ] Previous project's actions reviewed at this project's start. Done? yes / no

That last box is what makes the process visibly consequential rather than ceremonial. One agenda item, ten minutes.

# 7. Recurrence check

| Finding | Seen before on | How many times |
| --- | --- | --- |

A recurring finding is not a lesson: it is an unaddressed structural problem, and recording it again will not help. Escalate it as a decision needed, with an owner. Recurrence is useful evidence: it turns "we think this is a problem" into "this has now cost us three times".

# Sign-off

|  | Name | Date |
| --- | --- | --- |
| Facilitator |  |  |
| Project manager |  |  |
| Sponsor informed |  |  |
| Actions reviewed on |  |  |

Notice

This document is published by BvLogic as general reference material. It is provided for information only and is not professional, financial, legal or tax advice, and no liability is accepted for decisions taken on the basis of it. Figures in worked examples are illustrative unless a source is cited. Verify anything time-sensitive against the live version at bvlogic.com before relying on it.